{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":31,"n_cols":9,"rows_kept":31,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,2],[2,3,2,5],[2,7,2,8],[3,0,3,2],[3,3,3,5],[3,7,3,8],[4,0,5,2],[4,3,4,5],[4,6,4,8],[5,3,5,5],[5,6,5,8],[6,0,6,2],[6,3,6,5],[6,6,6,8],[7,0,8,0],[7,1,7,8],[8,1,8,8],[9,0,28,0],[9,1,9,3],[9,5,9,7],[10,1,17,3],[10,4,11,4],[10,5,10,7],[11,5,11,7],[12,4,14,4],[12,5,12,7],[13,5,13,7],[14,5,14,7],[15,4,16,4],[15,5,15,7],[16,5,16,7],[17,4,18,4],[17,5,17,7],[18,2,18,3],[18,5,18,7],[19,1,26,3],[19,5,19,7],[20,4,25,4],[20,5,20,7],[21,5,21,7],[22,5,22,7],[23,5,23,7],[24,5,24,7],[25,5,25,7],[26,5,26,7],[27,1,28,3],[27,5,27,7],[28,5,28,7],[30,0,30,8]]}
["扶贫项目资金绩效目标申报表"]
["（2018年度）"]
["项目名称",null,null,"沟渠硬化项目",null,null,"项目负责人及联系电话","邹登明13762096969"]
["主管部门",null,null,"区扶贫办",null,null,"实施单位","七弓岭管理站"]
["资金情况\n（万元）",null,null,"年度资金总额：",null,null,"15元"]
[{"$nulls":3},"         其中：财政拨款",null,null,"12万元，其中：2018年中央资金6万元、上年度退回中央资金2万元，市级资金4万元"]
[{"$nulls":3},"             其他资金",null,null,"自筹3万元"]
["总体目标","年度目标"]
[null,"通过对七弓岭管理站新建沟渠及硬化，增强排水量, 确保房屋不遭受水灾。"]
["绩效指标","一级指标",null,null,"二级指标","三级指标",null,null,"指标值"]
[null,"产出指标",null,null,"数量指标","沟渠硬化长度",null,null,"0.362KM"]
[{"$nulls":5},"沟渠宽度、高度",null,null,"底1M,高0.8M"]
[{"$nulls":4},"质量指标　","六合板",null,null,"289平米"]
[{"$nulls":5}," 混凝土强度",null,null,"C20"]
[{"$nulls":5},"机埠淸淤泥",null,null,"1200立方"]
[{"$nulls":4},"时效指标"," 开工时间",null,null,"2018-09-15"]
[{"$nulls":5}," 完工时间",null,null,"2018-11-15"]
[{"$nulls":4},"成本指标","水泥",null,null,"500元/吨"]
[{"$nulls":5},"裸石子",null,null,"3000元/车"]
[null,"效益指标",null,null,"经济效益指标"," 群众生产生活成本降低",null,null,"≥10%"]
[{"$nulls":5}," 受益行政村数",null,null,1]
[{"$nulls":5}," 受益村民小组数",null,null,1]
[{"$nulls":5}," 受益户数",null,null,"98户"]
[{"$nulls":5}," 受益人数",null,null,"275人"]
[{"$nulls":5}," 受益建档立卡户数",null,null,"14户"]
[{"$nulls":5}," 受益建档立卡人数",null,null,"31人"]
[{"$nulls":4},"可持续影响指标"," 该工程使用寿命",null,null,"≥10年"]
[null,"满意度指标",null,null,"服务对象"," 受益人口满意度",null,null,"≥99%"]
[{"$nulls":4},"满意度指标"," 受益贫困人口满意度",null,null,"≥99%"]
[]
[" 单位负责人：                   填表人：邹登明               上报日期：2018年11月29日"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}